## Rates
Rate | Value
Linear diffuser $/LF | 90
LF per diffuser | 4
Plenum box $/EA | 95
Branch $/EA | 45
VD/CO $/EA | 85
Mechanic MH per diffuser | 5.5
Mechanic $/MH | 125
Foreman $/HR | 155

## By area
Floor | Area | Location | LD qty | CFM | Material $ | Labor MH | Labor $ | Total $
29 | 29-1 | North-east corner, W 42nd St / Broadway | 4 | 1200
29 | 29-2 | Seventh Ave, north | 3 | 800
29 | 29-3 | Seventh Ave, Open Office 29.42 | 6 | 1600
29 | 29-4 | Broadway, north | 2 | 400
29 | 29-5 | Seventh Ave, south (north end of sheet B) | 4 | 1200
29 | 29-6 | Seventh Ave, south | 4 | 1200
30 | 30-1 | Seventh Ave, north | 3 | 800
30 | 30-2 | Seventh Ave, Open Office 30.35 | 5 | 1300
30 | 30-3 | South wall (W 41st St side) | 4 | 1200
31 | 31-1 | Seventh Ave, north (Focus Rm 31.65 / Corridor 31.51) | 2 | 400
31 | 31-2 | Seventh Ave, Huddle Rms 31.46 / 31.47 | 3 | 800
31 | 31-3 | Seventh Ave, at IDF 31.44 (match line) | 1 | 300
31 | 31-4 | Seventh Ave, 7P Meeting Rm 31.43 | 3 | 900
31 | 31-5 | Seventh Ave, south | 3 | 800
31 | 31-6 | Broadway, south | 2 | 600

## By floor
Floor | LD qty | Material $ | Labor $ | Foreman hr | Foreman $ | Air balancing $ | Shop drawings $ | Total $
29 |  |  |  | 30 |  | 2500 | 1500
30 |  |  |  | 15 |  | 1200 | 750
31 |  |  |  | 15 |  | 1200 | 750
Total